## Sheet1
Num | Progress | Feature | Description | Tech | Dependencies
1 | Not Started | Login with Facebook | simplify the login process by allowing login with Facebook credentials | Facebook embed
2 | Not Started | Share videos, playlists on Facebook | Embed Facebook like and share buttons on videos and playlists | Facebook embed | 1
3 | Not Started | Import Spotify Playlists | User clicks a button to recreate Spotify playlists in Elevate with existing videos in DB | Prob. a fuzzy text match on song and artist name
4 | Not Started | Search Playlists (instead of songs) | Playlists will populate the screen as a result of a query just as songs currently do | Same infrastructure as song search, just need added DB features | 3?
5 | Not Started | Suggested search terms | will autopopulate a list of popular search terms that begin / contain / are similar to the string the user is typing in | Text match with DB entries sorted by pop., would be better with fuzzy text match
6 | Not Started | Trending videos | video sort on acceleration of view count | same infrastructure, simple algorithm
7 | Not Started | Artist Search | Click artist name to search their videos | need to re-implement with unique artist id
8 | Not Started | Related videos | Display videos related to a playing video | Possibly pull relationships from youtube/spotify, otherwise go off of spotify playlists
9 | Not Started | Staff Picks | allow staff to select songs to curate a user experience | was working, need to fix bug
10 | Not Started | connect blog and video entries | blog entries do not necessarily enter a song into the song search DB, need to fix this | merge blog and song entry forms, make some fields optional
11 | Not Started | scrub genre classifications | Genres need to be more intuitive, many songs don't fit well, are missing classifications like "sexy" | Infrastructure is there, non-tech issue
12 | Not Started | add site security | will need to protect every user-input field | will likely need to hash user input strings
13 | Not Started | Link URLs to playing videos | Allow links to point directly to a video for purposes of sharing online